DOUGH BABIES

6-Week Direct Sales Campaign

Every child deserves a doll that looks like them.

Prepared by P5 Marketing  •  March 2026

Client: Cute C Toys, LLC  •  cutectoys.com

Budget: $6,000 over 6 weeks ($1,000 ad spend + P5 services + Audience Lab)

# 1. Campaign Overview

Campaign Name: "Adopt a Dough Baby" — 6-Week Direct Sales Sprint

Summary: A six-week, intent-driven campaign combining targeted display ads, email nurture sequences, and social content to drive direct sales of Dough Babies plush dolls ($69 single / $99 twins) through cutectoys.com, leveraging Audience Lab’s intent data to reach parents and gift buyers most likely to convert.

Primary Objective

Generate 80–120 direct sales through cutectoys.com over 6 weeks, producing $5,500–$8,300 in gross revenue from a $1,000 ad spend (5.5–8.3x ROAS target).

Secondary Objectives

• Build email list to 500+ subscribers for Shark Tank episode amplification

• Establish retargeting pixel data on 2,000+ qualified visitors

• Generate 15–20 pieces of user-generated content (UGC) from customers

• Test messaging and audience segments for future scaled campaigns

# 2. Target Audience

Primary Segment: Gift-Giving Parents & Grandparents

• Women 28–55, household income $60K+

• Parents of children ages 0–8, grandparents shopping for young grandchildren

• Values: safety, inclusivity, quality, meaningful gifts over disposable toys

• Pain point: "Most toys are cheap plastic junk with questionable materials"

• Buying triggers: birthdays, baby showers, holidays, "just because" gifting

Secondary Segment: Inclusive/Conscious Gift Buyers

• Adults 25–45 buying for nieces, nephews, godchildren, friends’ kids

• Actively seek diverse, inclusive products that represent all children

• Willing to pay premium for quality, safety-tested, and meaningful toys

• Often discover products through social media and word-of-mouth

Where They Spend Time

• Instagram (discovery + shopping), Facebook (parenting groups, gifting ideas)

• Pinterest (gift ideas, nursery planning, baby shower inspiration)

• Parenting blogs, mommy influencer content, toy review sites

• Google Shopping and Amazon browsing for "unique baby gifts" and "inclusive dolls"

Audience Lab Intent Signal: We’ll target users actively searching for baby gifts, plush toys, inclusive children’s products, and related intent keywords — reaching them with display ads before they’ve found Dough Babies organically.

# 3. Key Messages

Core Campaign Message

"Dough Babies are the safe, inclusive, irresistibly squishable dolls that every child deserves — and every parent can trust."

Supporting Messages

1. Safety First: "Created by a 14-year-old and his surgeon father after discovering toxic chemicals in his sister’s toys. Every Dough Baby is third-party tested to CE, ASTM, and CPSIA standards."

2. Inclusivity: "Available in a range of skin tones so every child can find a doll that looks like them. Because representation starts at playtime."

3. Premium Quality: "Hand-sewn details, embroidered features (no choking hazards), ultra-soft plush exterior. This isn’t a $10 toy — it’s a keepsake."

4. Founder Story: "A Houston teen turned concern for his sister into a nationally recognized toy brand. Every purchase supports children’s charities."

Message by Channel

| Channel | Tone | Lead Message |
| --- | --- | --- |
| Display Ads | Warm, visual, curiosity-driven | "Meet the safest, squishiest doll your kid will ever love." |
| Email | Personal, story-driven, trust-building | "Why a 14-year-old created the toy your child deserves." |
| Social | Fun, inclusive, UGC-forward | "Tag us with #MyDoughBaby for a chance to be featured!" |
| Retargeting | Urgency + social proof | "Twins are better together — grab two for $99." |

# 4. Channel Strategy

## 4a. Display Ads via Audience Lab (Primary Driver)

Why: Audience Lab’s intent data lets us reach parents and gift buyers who are actively researching baby gifts, plush toys, and inclusive children’s products — before they discover competitors.

Format: Static and animated display banners (300x250, 728x90, 320x50) featuring Dough Baby product shots with emotional copy.

Budget: $600 of the $1,000 ad budget (~$100/week).

Targeting: Intent audiences for "baby shower gifts," "inclusive dolls," "non-toxic toys," "unique children’s gifts," "plush dolls for kids."

## 4b. Email Nurture via Audience Lab

Why: Retarget website visitors and intent-matched prospects who didn’t convert on first touch. Email has the highest ROI for DTC at this price point.

Format: 3-email welcome sequence + 2-email retargeting sequence.

Budget: Included in Audience Lab platform cost.

## 4c. Social Media (Organic)

Why: Instagram and Facebook are primary discovery channels for this demographic. UGC and founder story content builds trust and shareability.

Format: 3–4 posts/week: product photos, founder story clips, customer UGC, "Meet the Dough Babies" character reveals.

Budget: $0 (organic). $200 for 2–3 boosted posts on best-performing content.

## 4d. Retargeting Pixel

Why: Capture visitors from display ads and organic traffic, then retarget with conversion-focused messaging.

Format: Dynamic retargeting ads showing the specific Dough Baby collection they viewed.

Budget: $200 of ad budget for retargeting spend.

## Budget Allocation Summary

| Channel | 6-Week Spend | % of Ad Budget | Expected Role |
| --- | --- | --- | --- |
| Display (Audience Lab) | $600 | 60% | Top-of-funnel awareness + traffic |
| Retargeting | $200 | 20% | Mid-funnel conversion |
| Boosted Social Posts | $200 | 20% | Engagement + social proof |
| Email (Audience Lab) | Included | — | Nurture + conversion |
| Organic Social | $0 | — | Brand building + UGC |
| TOTAL AD SPEND | $1,000 | 100% |  |

# 5. Six-Week Content Calendar

## Week 1: Foundation & Launch

Theme: "Meet the Dough Babies"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | Install retargeting pixel on cutectoys.com | Website | Must be live before ads start |
| Mon | Launch display ad campaign (Audience Lab) | Display | 3 ad variants, intent audiences |
| Tue | Welcome email sequence goes live | Email | Triggered by new subscriber/visitor |
| Wed | "Meet the Dough Babies" carousel post | Instagram/FB | Introduce each doll in the collection |
| Thu | Founder story post: Colton’s origin story | Instagram/FB | Photo of Colton + dolls |
| Fri | "Why we test every doll" safety infographic | Instagram/FB | CE, ASTM, CPSIA badges |

## Week 2: Social Proof & Trust

Theme: "Real Families, Real Dough Babies"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | Customer spotlight / first UGC repost | Instagram/FB | Ask early buyers for photos |
| Wed | "Twins Deal" promotional email | Email | Highlight $99 twin bundle |
| Wed | Behind-the-scenes: How Dough Babies are made | Instagram Reels | Show hand-sewn details |
| Fri | Boost top-performing post from Week 1 | Paid Social | $75 boost budget |
| Ongoing | Monitor display ad performance, adjust targeting | Audience Lab | Kill underperforming variants |

## Week 3: Emotional Connection

Theme: "Every Child Deserves to Be Seen"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | Inclusivity-focused post: diverse doll lineup | Instagram/FB | Representation messaging |
| Tue | Retargeting email to non-converters | Email | "Still thinking about it?" + twin deal |
| Wed | ABC7 news feature reshare | Instagram/FB/Stories | Third-party credibility |
| Thu | "Gift Guide" content: top occasions for a Dough Baby | Blog/Social | Baby showers, birthdays, holidays |
| Fri | UGC contest launch: #MyDoughBaby | Instagram | Feature winners on main feed |

## Week 4: Conversion Push

Theme: "Adopt Your Dough Baby Today"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | Refresh display ad creative (new variants) | Audience Lab | Prevent ad fatigue |
| Tue | "Adoption Certificate" feature post | Instagram/FB | Show the unboxing experience |
| Wed | Limited-time offer email: free shipping or bonus | Email | Create urgency |
| Thu | Customer testimonial video / quote graphic | Instagram/Social | Social proof |
| Fri | Boost best post from Weeks 2–4 | Paid Social | $75 boost budget |

## Week 5: Scale What Works

Theme: "The Gift That Means Something"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | Double down on best-performing display audience | Audience Lab | Reallocate budget to winners |
| Tue | "Gift for someone special" email to full list | Email | Position as thoughtful gift |
| Wed | UGC roundup: best #MyDoughBaby submissions | Instagram/FB | Community building |
| Thu | Colton Q&A or short interview video | Instagram Reels/TikTok | Humanize the brand |
| Fri | Retargeting push to all pixel audiences | Retargeting | Final conversion window |

## Week 6: Final Sprint & Wrap-Up

Theme: "Last Chance + What’s Next"

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Mon | "Final week" urgency email | Email | Last chance for any active promo |
| Tue | Sneak peek: upcoming collections (Mythicals, Animals) | Instagram/FB | Future excitement |
| Wed | Thank you post to community + UGC highlights | Instagram/FB | Gratitude + social proof |
| Thu | Campaign performance review (internal) | P5 Internal | Compile results for client |
| Fri | Wrap-up report delivered to Cute C Toys | P5 Deliverable | Insights + next steps |

# 6. Content Assets Required

| Asset | Type | Priority | Deadline |
| --- | --- | --- | --- |
| Display ad set (3 variants, 3 sizes each) | Static/Animated Banners | Must-have | Week 1 Day 1 |
| Welcome email sequence (3 emails) | Email Copy | Must-have | Week 1 Day 2 |
| Retargeting email sequence (2 emails) | Email Copy | Must-have | Week 3 |
| Product photography (lifestyle shots) | Photography | Must-have | Pre-launch |
| Founder story content (photo + copy) | Social Post | Must-have | Week 1 |
| Safety/testing infographic | Graphic | Must-have | Week 1 |
| "Twins Deal" promotional graphics | Social/Email | Must-have | Week 2 |
| #MyDoughBaby UGC contest rules + graphics | Social | Nice-to-have | Week 3 |
| Gift guide blog post or landing page | Web Content | Nice-to-have | Week 3 |
| Customer testimonial quotes/graphics | Social | Nice-to-have | Week 4 |
| Colton Q&A video (60–90 seconds) | Video | Nice-to-have | Week 5 |
| Refreshed display ad creative (round 2) | Banners | Must-have | Week 4 |
| Campaign wrap-up report | PDF/DOCX | Must-have | Week 6 |

# 7. Success Metrics & KPIs

Primary KPI

Direct sales through cutectoys.com: Target 80–120 units over 6 weeks

Secondary KPIs

| Metric | Target | Tracking Method |
| --- | --- | --- |
| Website visitors (from campaign) | 3,000–5,000 | Google Analytics UTM tracking |
| Email list growth | 500+ new subscribers | Audience Lab / Shopify |
| Display ad CTR | 0.3–0.5% | Audience Lab dashboard |
| Email open rate | >25% | Audience Lab |
| Email click rate | >3.5% | Audience Lab |
| Retargeting conversion rate | 2–4% | Pixel tracking |
| Social engagement rate | >4% | Instagram/FB insights |
| UGC submissions (#MyDoughBaby) | 15–20 posts | Hashtag monitoring |
| Cost per acquisition (CPA) | <$12.50 | Ad spend / conversions |
| ROAS (return on ad spend) | 5.5–8.3x | Revenue / $1,000 ad spend |

Reporting cadence: Weekly performance snapshots (every Friday) + full wrap-up report at Week 6. P5 will monitor Audience Lab dashboard daily during Weeks 1–2 for rapid optimization.

# 8. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Low initial traffic from display ads | Medium | High | Test 3 ad variants in Week 1, kill losers fast, reallocate to winners by Week 2 |
| High CPA due to premium price point ($69) | Medium | Medium | Lead with twins deal ($99/2 = $49.50 each) in retargeting; emphasize value over price |
| Insufficient UGC from early customers | Medium | Low | Seed UGC with product-to-influencer gifting (2–3 micro-influencers in parenting niche) |
| Ad fatigue after 3–4 weeks | High | Medium | Refresh creative at Week 4; rotate messaging angles (safety → inclusivity → founder story) |
| Shark Tank date announced mid-campaign | Low | High (positive) | Pivot immediately to pre-episode buzz campaign; reallocate remaining budget to awareness |

# 9. Immediate Next Steps

Week -1 (Pre-Launch Checklist):

| Action | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Confirm retargeting pixel is installed on cutectoys.com | P5 / Robert | Before Week 1 | Pending |
| Set up Audience Lab campaign with intent audiences | P5 / Robert | Before Week 1 | Pending |
| Design display ad creative (3 variants x 3 sizes) | P5 / Designer | Before Week 1 | Pending |
| Write welcome email sequence (3 emails) | P5 | Before Week 1 | Pending |
| Gather product photography from Cute C Toys | Client / Colton | Before Week 1 | Pending |
| Confirm social media account access | P5 / Client | Before Week 1 | Pending |
| Set up UTM tracking parameters | P5 / Robert | Before Week 1 | Pending |
| Brief client on campaign plan and get approval | P5 / Robert | This week | In Progress |

Note on Shark Tank: This campaign is designed to stand on its own as a direct sales engine. However, if the air date is confirmed during the campaign, we can instantly pivot to a pre-episode buzz strategy — the retargeting pixel data, email list, and display infrastructure we build now become the foundation for a massive Shark Tank amplification push.

— End of Campaign Plan —

Prepared by P5 Marketing for Cute C Toys, LLC